## BackLog
THE APPLICATION DEVELOPMENT PROJECT TOPIC (SWP391)
ASSIGNMENT FUNCTION DETAILS - ONLINE SHOPPING SYSTEM
Project: Online Shop
# | Feature | Function/Screen Details | Iteration | Deadline | In Charge | Status | Estimate | Level | LOC
1 | Home Page | It allow everyone can view and search product in website | Iteration 1 | 2021-10-07 | Trần Văn Đức | Completed |  | Medium | 120
2 | Product List | Customer can see products that they have just searched | Iteration 1 | 2021-10-07 | Bạch Ngọc Minh Châu | Completed |  | Complex | 240
3 | Product Details | Details like description, color, size, ... for customer to choose | Iteration 1 | 2021-10-07 | Nguyễn Duy Mạnh | Completed |  | Medium | 120
4 | Cart Details | List of all the products that have been added into the cart | Iteration 1 | 2021-10-17 | Bạch Ngọc Minh Châu | Completed |  | Medium | 120
5 | User Login | User will login with account | Iteration 1 | 2021-10-07 | Nguyễn Gia Phú | Completed |  | Simple | 60
6 | User Register | Customer can register a new account here | Iteration 1 | 2021-10-07 | Nguyễn Gia Phú | Completed |  | Simple | 60
7 | User List | Admin manage accounts | Iteration 1 | 2021-10-07 | Đinh Tiến Lâm | Completed |  | Medium | 120
8 | Customers List[Seller] | Show list of all customer | Iteration 2 | 2021-10-17 | Nguyễn Duy Mạnh | Completed |  | Simple | 60
9 | Cart Completion (Place Order) | Customer can comfirm order information like shipping information,... or change it | Iteration 2 | 2021-10-17 | Bạch Ngọc Minh Châu | Completed |  | Complex | 240
10 | Reset Password | User can retrieve password when forgotten by confirming information via email | Iteration 2 | 2021-10-07 | Trần Văn Đức | Completed |  | Medium | 120
11 | Change Password | It allow user can change new password | Iteration 2 | 2021-10-07 | Đinh Tiến Lâm | Completed |  | Simple | 60
12 | User Profile | User can view and update user's infomation | Iteration 2 | 2021-10-07 | Đinh Tiến Lâm | Completed |  | Simple | 60
13 | My Orders (xem lịch sử order) (Tổng quát) | Customers can view history of orders | literation 3 | 2021-10-17 | Đinh Tiến Lâm | Completed |  | Simple | 60
14 | Order Information | Buyer views the detail of 1 of his orders | literation 3 | 2021-10-17 | Đinh Tiến Lâm | Completed |  | Medium | 120
15 | Products List [Sale] | seller views and manages all products | literation 3 | 2021-10-17 | Nguyễn Gia Phú | Completed |  | Medium | 120
16 | Orders List [Sale] | Admin views list of all of orders | literation 3 | 2021-11-06 | Trần Văn Đức | Completed |  | Simple | 60
17 | Order Details [Sale] | The seller can see the orders, they can approve the order or not | literation 3 | 2021-11-06 | Trần Văn Đức | Completed |  | Simple | 60
18 | Feedback | User can view feedback from other customer about a product | literation 3 | 2021-10-17 | Nguyễn Duy Mạnh | Completed |  | Simple | 60
19 | Blogs List | List of all the blogs for visitor to read | literation 3 | 2021-10-07 | Ngô Thị Ngọc Mai | Completed |  | Simple | 60
20 | Blog Details | Content of a blog | literation 3 | 2021-10-07 | Ngô Thị Ngọc Mai | Completed |  | Simple | 60
21 | Blog Management | CRUD for Blog | literation 3 | 2021-11-06 | Ngô Thị Ngọc Mai | Completed |  | Simple | 60
22 | Notification | Show news about your order, replies,... | literation 3 | 2021-11-06 | Bạch Ngọc Minh Châu | Completed |  | Simple | 60
23 | Dashboard | Seller views Statistic of the sale of his products | literation 3 | 2021-11-06 | Nguyễn Gia Phú + Trần Văn Đức | Completed |  | Medium | 120
24 | Error | Placeholder when error occur | literation 3 | 2021-11-06 | Bạch Ngọc Minh Châu | Completed |  | Simple | 60
25 | About Shope | Contains information with embedded google map and current recruitment information | literation 3 | 2021-11-06 | Đinh Tiến Lâm | Completed |  | Simple | 60
26 | Post List | Show list of all post | literation 3 | 2021-11-06 | Nguyễn Gia Phú | Completed |  | Medium | 120
27 | Post Details | Show details of post | literation 3 | 2021-11-06 | Nguyễn Gia Phú | Completed |  | Medium | 120
28 | Authoriation | User Authoriation for system | literation 3 | 2021-11-06 | Bạch Ngọc Minh Châu | Completed |  | Complex | 240
29 | Ship-work |  | literation 3 | 2021-11-06 | Trần Văn Đức | Completed |  | Simple | 60
30 | Dashboard | Seller views Statistic of the sale of his products | literation 3 | 2021-11-06 | Trần Văn Đức | Completed |  | Simple | 60
31 | Manager Feedback [Seller] | Seller can view and reply | literation 3 | 2021-11-06 | Ngô Thị Ngọc Mai | Completed |  | Simple | 60
32 | Manager Feedback [Customer] | Customer views Feedback, edits feedback of product | literation 3 | 2021-11-06 | Ngô Thị Ngọc Mai | Completed |  | Simple | 60
33 | Manager banner | MK can manager banner and customer can view bannẻ | literation 3 | 2021-11-06 | Bạch Ngọc Minh Châu | Completed |  | Simple | 60
Time | Notes (Task Details, etc.) | Link Google Meet | Mentor | Recording Link
14h30 - 16h (15/09/2021) | FrontEnd_Boostrap 5.0.2 | Link | Bạch Ngọc Minh Châu | Link Record
13/09/2021-17/09/2021 | Complete requirements and database | Link | All member
21h-22h30(16/09/2021) | JSP + servlet | Link | Trần Văn Đức | Link Record
21h-22h30(17/09/2021) | Systax | Link | Đinh Tiến Lâm | Link Record
20h30-9h30(27/09/2021 | Syntax | Link | Trần Văn Đức | Link Record